## 1. Product Overview
Item | Description
Product Name | GlowUp
Product Vision/ Purpose | To help users improve their body and facial appearance through a simple, structured 30-day fitness and glow-up plan with guided exercises and progress tracking.
Business Goals / Key Success factors | Help users stay consistent, provide structured plans, increase motivation, improve engagement, and boost user confidence
Primary Stakeholders | Development team,Faculty/Project evaluators,Users (students and young professionals)

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up so that I can access the app. | Registration screen details | Must Have | 8 | To Do | Aditya | Verify user registration | Arun
|  |  |  | Email input |  |  |  | Achal |  | Ankit
Login screen
Firebase authentication
Login Error Screen
E2 | Dashboard | US2 | As a user, I want to select a 30-day challenge so that I can start my transformation. | Challenge selection screen | Must Have | 8 | In Progress | Anish | Check challenge selection | Arun
|  |  |  | 30-day plan display | Must Have |  |  | Aditya |  | Ankit
Anoop
E3 | Daily Excersices | US3 | As a user, I want to view daily exercises so that I can follow my routine. | Exercise list screen | should have | 8 | to Do | Anish | Verify exercises are shown correctly | Arun
|  |  |  | Daily workout display | Must have |  |  | Anoop |  | Ankit
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | User Authentication, Basic App Setup | Firebase setup | On Track
v0.2 | 2025-11-22 | 30-Day Challenge Selection, Daily Exercise Display | UI implementation | Planned
v0.3 | 2025-11-29 | Progress Tracking System, Completion Tracking | Firebase database integration | Planned
v0.4 | 2025-12-06 | Guided Structured Plan (Step-by-step flow), UI Improvements | Frontend integration | Planned
v0.5 | 2025-12-13 | Improved User Experience, Bug Fixing, Testing | Testing feedback | Yet to Plan
v1.0 | 2025-12-20 | Complete Working Prototype (30-day challenge + exercises + progress tracking) | All modules integrated | Yet to Plan
v1.1 | 2025-12-27 | Diet Plan Recommendations, Notifications, Analytics Dashboard | Advanced backend support | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead